## TrustL
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
As of 2nd QUARTER, CY 2020
Silay City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
LGSF-BUB Feb 2016 |  | 3400000
Renovation of Brgy. Health Center -Had. Daniel | Brgy. E. Lopez | 873989 | 2018-01-03 |  | 100% | 873720.18
Renovation of Brgy. Health Center - Brgy. Patag | Brgy. Patag | 622209 | 2017-12-28 |  | 100% | 611970.28
Renovation of Brgy. Health Center - Brgy. Kapt. Ramon | Brgy. Kapt. Ramon | 700489 | 2017-11-06 |  | 100% | 679437.05
Construction of School Clinic | DMLMHS | 1120000 |  |  |  | 0 |  | cancelled POW
DILG - PCF |  | 5800000
2016 PCF - Purchase of Tourist Bus | Silay City LGU | 3400000 |  |  | 100% | 3400000
2017 PCF - Construction of Tourist Information Center | Rizal-Zulueta Sts. | 2400000 |  |  | 100% | 2400000 | counterpart- | ongoing
2018 PCF - Purchase of Vehicle | Silay City LGU | 5100000 |  |  | 100% | 5100000
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
sgd |  | sgd |  |  | sgd
RAMON H. DUMANCAS | EMMANUEL S. ARSENAL |  |  |  | MARK ANDREW ARTHUR J. GOLEZ
City Budget Officer | City Accountant |  |  |  | City Mayor