## Trust Fund Utilization
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
FOR THE 1ST QUARTER, CY 2018
Silay City
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
LGSF-BUB Feb 2016 |  | 3400000
Renovation of Brgy. Health Center -Had. Daniel | Brgy. E. Lopez | 873989 | 2018-01-03 |  |  | 679001.06
Renovation of Brgy. Health Center - Brgy. Patag | Brgy. Patag | 622209 | 2017-12-28 |  |  | 403829.4
Renovation of Brgy. Health Center - Brgy. Kapt. Ramon | Brgy. Kapt. Ramon | 700489 | 2017-11-06 |  |  | 607068.9
Construction of School Clinic - DMLMHS |  | 1120000 | no movement |  |  | 0
DILG - PCF |  | 5800000
2016 PCF - Purchase of Tourist Bus (PO94) 3/26/18 |  | 3400000 |  |  |  | 3400000
2017 PCF |  | 2400000 | no movement |  |  | 0
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
sgd |  |  |  |  | sgd
EMMANUEL S. ARSENAL |  |  |  |  | MARK ANDREW ARTHUR J. GOLEZ
City Accountant |  |  |  |  | City Mayor